## Document Control
Santa Laukmane — ISMS Portfolio Project — Fictional Organization
Classification: Confidential
AETHERIA INFRASTRUCTURE RESEARCH (AIR)
Information Security Risk Register ¦ AIR-ISMS-RSK-002
Document ID | AIR-ISMS-RSK-002
Version | 1.0
Status | Draft — Pending Management Approval
Classification | Confidential
Document Owner | Head of Security & Compliance
Approved By | Chief Executive Officer
Review Cycle | Quarterly / Annual full review each May
Last Reviewed | 2026-05-01
Next Review Due | August 2026 (quarterly) / May 2027 (annual)
Methodology | AIR-ISMS-RSK-001 Risk Assessment Methodology
Asset Inventory | AIR-ISMS-AST-001 Information Asset Inventory
Applicable Standard | ISO/IEC 27001:2022 — Clauses 6.1.2 and 6.1.3
HOW TO USE THIS REGISTER
Risk Register tab | Contains all active and accepted risks. Each row is one risk scenario linked to a primary asset from AIR-ISMS-AST-001.
Inherent Risk Score | Likelihood × Impact before controls are applied. Reflects the raw exposure.
Residual Risk Score | Likelihood × Impact after existing and planned controls. This is the score used for acceptance decisions.
Treatment Actions column | Describes what must be done to achieve the residual score. Actions should be tracked in Jira.
Status field | Open = no treatment started. In Progress = treatment underway. Accepted = risk tolerated within appetite. Closed = risk resolved or eliminated.
Review cadence | Risk Register reviewed quarterly. Individual risk owners update status before each review. Full reassessment annually in May.
Adding new risks | New risks are added following the methodology in AIR-ISMS-RSK-001. Notify Head of Security & Compliance before adding entries.

## Risk Register
Santa Laukmane — ISMS Portfolio Project — Fictional Organization
Classification: Confidential
AETHERIA INFRASTRUCTURE RESEARCH (AIR) ¦ Information Security Risk Register
AIR-ISMS-RSK-002 v1.0 ¦ Classification: Confidential ¦ Owner: Head of Security & Compliance ¦ Last Reviewed: May 2025
ASSET |  |  | RISK IDENTIFICATION |  |  | INHERENT RISK |  |  |  | RISK TREATMENT |  |  | RESIDUAL RISK |  |  | TRACKING
Risk ID | Asset ID | Asset Name | Threat Scenario | Vulnerability | Existing Controls | Likelihood (1–5) | Impact (1–5) | Inherent Score | Inherent Level | Treatment Option | Planned Treatment Actions | Risk Owner | Residual Likelihood | Residual Impact | Residual Score | Residual Level | Target Date | Status | Last Reviewed | Notes
RSK-001 | PA-001 / PA-002 | Government-Affiliated Research Data | Contractor with excessive permissions accesses Restricted research data outside their authorised scope. | No formal access review process. Contractor accounts not differentiated from employee accounts in RBAC assignments. | Entra ID authentication. Basic RBAC configured. Conditional Access policies partially applied. | 4 | 4 | 16 | High | Treat | Implement quarterly contractor access reviews. Enforce principle of least privilege for all contractor accounts. Create a dedicated contractor security group with restricted permissions. Document approved access scope per contractor. | Head of IT Operations | 2 | 4 | 8 | Medium | 30 Sep 2026 | In Progress | May 2026 | Access review process drafted. Implementation pending IT resource allocation.
RSK-002 | PA-006 / Cross-cutting | Security Configurations & Credentials | Threat actor compromises user credentials via phishing and gains access to AIR systems due to absent or inconsistent MFA enforcement. | MFA not enforced for all user accounts via Conditional Access. Legacy system exceptions exist. MFA coverage not monitored. | MFA available in Entra ID. Password complexity policy enforced. Some Conditional Access policies active. | 4 | 4 | 16 | High | Treat | Enforce MFA via Conditional Access for all accounts with no exceptions. Eliminate legacy authentication protocols. Report MFA coverage metric monthly to Head of Security & Compliance. Conduct phishing simulation annually. | Head of IT Operations | 2 | 4 | 8 | Medium | 31 Jul 2026 | In Progress | May 2026 | Conditional Access policy drafted. Legacy protocol audit in progress. Target: 100% MFA coverage.
RSK-003 | PA-001 / PA-002 | Critical Infrastructure Analysis Datasets | Misconfigured Azure Blob Storage container allows public or unauthenticated access to Restricted research datasets. | No automated configuration scanning in place. Manual review process is inconsistent. Configuration drift not monitored. | Network isolation on research containers. Access logging enabled. Azure Monitor partially configured. | 3 | 5 | 15 | High | Treat | Deploy Azure Policy to deny public blob access organisation-wide. Enable Microsoft Defender for Storage. Implement weekly automated configuration scan. Remediate any public containers within 24 hours of detection. | Head of IT Operations | 1 | 5 | 5 | Medium | 31 Aug 2026 | Open | May 2026 | Azure Policy definition drafted. Awaiting approval to deploy to air-prod tenant.
RSK-004 | PA-001 / PA-002 / PA-003 | Restricted Research & AI Model Data | Employee or contractor uploads Restricted research data or AI model artefacts to an unsanctioned AI service (e.g., public large language model). | No policy prohibiting unsanctioned AI tool use. No endpoint DLP controls on data transfers to cloud AI services. Limited user awareness of AI-specific data risks. | DLP policies active on Exchange Online. Sensitivity labels configured in Microsoft 365. Acceptable Use Policy does not currently address AI tools. | 4 | 4 | 16 | High | Treat | Publish AI Tool Acceptable Use Policy. Implement endpoint DLP to block file uploads to unsanctioned AI services. Establish and communicate an approved AI tools list. Deliver targeted security awareness module on AI tool risks. | Head of Security & Compliance | 2 | 4 | 8 | Medium | 31 Oct 2026 | Open | May 2026 | AI AUP in draft. DLP rule design underway. Approved tools list being compiled with R&D and AI Engineering.
RSK-005 | Cross-cutting | All Primary Assets (access vector) | Departed employee or contractor retains active system access after termination, enabling unauthorised access or data exfiltration. | No automated offboarding workflow. HR and IT processes not integrated. Contractor offboarding handled inconsistently across departments. | Entra ID manages access centrally. Manual offboarding checklist exists. IT Operations notified via email by HR. | 4 | 4 | 16 | High | Treat | Automate account deprovisioning via HR system integration with Entra ID. Implement 24-hour offboarding SLA. Conduct quarterly review of accounts inactive for over 30 days. Audit contractor account termination dates against HR records. | Head of IT Operations | 1 | 4 | 4 | Low | 30 Sep 2026 | Open | May 2026 | HR system integration scoping underway. Interim: manual checklist enforcement confirmed with all department heads.
RSK-006 | PA-005 | Incident Investigation Evidence | Security incident occurs but is not detected in a timely manner due to insufficient log coverage and alert tuning. | Not all in-scope systems feed logs into Azure Monitor. No SIEM alert rules tuned for AIR-specific threat scenarios. Log retention not consistently enforced. | Azure Monitor / Log Analytics Workspace in place. Some alerting configured. Security team reviews alerts manually. | 3 | 4 | 12 | High | Treat | Extend log collection to all in-scope systems. Define and implement detection rules for critical threat scenarios (credential theft, bulk download, after-hours access). Set minimum 90-day log retention. Conduct quarterly alert rule review. | Head of IT Operations | 2 | 3 | 6 | Medium | 30 Nov 2026 | Open | May 2026 | Log source inventory complete. Alert rule backlog prioritised. Retention policy configuration in progress.
RSK-007 | PA-003 / PA-004 | AI Model Weights & Source Code | Disgruntled or departing employee exfiltrates proprietary AI model weights or source code via personal cloud storage or personal devices. | No DLP controls on endpoint transfers to personal cloud storage. No alerting for anomalous large-volume downloads from GitHub or Azure ML. Limited behavioural monitoring. | GitHub Enterprise branch protection and audit logs. Intune managed endpoints. Sensitivity labels in M365. HR offboarding process. | 2 | 5 | 10 | High | Treat | Implement endpoint DLP to restrict transfers to personal cloud storage from managed devices. Enable anomalous download alerting in GitHub Enterprise. Enforce sensitivity label-based access restrictions on model artefacts. Include IP exfiltration scenario in annual tabletop exercise. | Head of Security & Compliance | 1 | 5 | 5 | Medium | 31 Dec 2026 | Open | May 2026 | GitHub audit log alerting in scope for RSK-006 detection rule work. Endpoint DLP design underway.
RSK-008 | PA-001 / PA-002 / PA-007 | Research Data & Partner Agreements | A supplier or research contractor with access to AIR data suffers a breach, resulting in exposure of AIR Confidential or Restricted information. | No formal supplier security assessment process. Security requirements absent from some legacy supplier agreements. No periodic review of supplier security posture. | NDAs in place for most suppliers. Some contractual data handling clauses. Basic onboarding checks conducted by Legal & Partnerships. | 3 | 4 | 12 | High | Treat | Develop and implement a supplier security questionnaire for all suppliers handling Restricted or Confidential data. Add mandatory security clauses to all new contracts. Classify suppliers by risk tier. Conduct annual review of Tier 1 (highest-risk) suppliers. | Head of Legal & Partnerships | 2 | 3 | 6 | Medium | 31 Jan 2026 | Open | May 2026 | Supplier tier classification in progress. Security questionnaire template in draft.
RSK-009 | PA-001 / PA-002 / SA-008 | Research Data Repositories (cloud & on-premises) | Ransomware attack encrypts research data repositories, rendering active datasets unavailable and potentially exfiltrating data prior to encryption. | On-premises research repositories (SA-008) not covered by automated backup verification. Endpoint detection coverage may have gaps. No tested recovery playbook for ransomware. | Azure Backup for cloud workloads. Intune endpoint management. Microsoft Defender for Endpoint deployed on managed endpoints. | 3 | 5 | 15 | High | Treat | Implement immutable backup for on-premises repositories. Verify cloud backup restoration quarterly via test restoration. Confirm Defender for Endpoint coverage on 100% of managed fleet. Develop and test a ransomware recovery playbook. Conduct annual ransomware tabletop exercise. | Head of IT Operations | 2 | 4 | 8 | Medium | 31 Oct 2026 | Open | May 2026 | Immutable backup solution selected. Implementation scheduled for Q3 2026.
RSK-010 | PA-001 / PA-002 / PA-010 | Government & Internal Research Data | Contractor accesses AIR systems from an unmanaged personal device, bypassing endpoint security controls enforced on managed devices. | Personal devices excluded from ISMS scope but not technically prevented from accessing AIR systems. No device compliance check enforced in Conditional Access for contractor accounts. | Entra ID authentication. Conditional Access policies partially deployed. Intune MDM for corporate fleet. | 4 | 3 | 12 | High | Treat | Enforce device compliance check in Conditional Access for all user accounts. For contractors requiring Restricted data access: provision AIR-managed devices or implement browser-based isolation via Azure Virtual Desktop. Review contractor device access quarterly. | Head of IT Operations | 2 | 3 | 6 | Medium | 30 Nov 2026 | Open | May 2026 | Conditional Access device compliance rule in design. Azure Virtual Desktop licensing under evaluation.
RSK-011 | PA-001 / PA-007 | Research Data & Contract Agreements | Employee inadvertently emails Restricted or Confidential data to an incorrect or external recipient due to auto-complete or insufficient DLP controls. | DLP policies do not cover all Restricted data types. User awareness of data classification handling requirements is incomplete. No external email warning banners deployed. | DLP policies on Exchange Online for sensitivity-labelled content. Sensitivity labels in Microsoft 365. Basic security awareness training delivered at onboarding. | 3 | 3 | 9 | Medium | Treat | Strengthen DLP policy to require confirmation before sending externally for Restricted-labelled content. Enable external recipient warning banners in Exchange Online. Deliver targeted awareness training on data classification and email handling. Review DLP policy effectiveness quarterly. | Head of Security & Compliance | 2 | 2 | 4 | Low | 31 Aug 2026 | In Progress | May 2026 | DLP policy update in testing. External warning banner configuration completed in dev tenant.
RSK-012 | PA-010 / PA-011 | Internal Research & Project Data | Managed endpoint is lost or stolen at a conference or in transit, resulting in unauthorised access to locally cached data. | BitLocker enforcement not verified across 100% of the managed fleet. Remote wipe process not tested regularly. No travel security briefing for staff attending external events. | Intune MDM enrollment. BitLocker policy configured and deployed. Remote wipe available via Intune. Screen lock enforced. | 2 | 3 | 6 | Medium | Treat | Verify BitLocker enforcement on 100% of fleet via Intune compliance report. Test remote wipe process quarterly and document results. Issue travel security briefing to all staff attending conferences or field visits with managed devices. | Head of IT Operations | 1 | 2 | 2 | Low | 31 Jul 2026 | In Progress | May 2026 | BitLocker compliance report pulled: 96% coverage. 6 devices flagged for remediation. Travel briefing template drafted.
RSK-013 | PA-008 | Employee & Contractor HR Records | Personal data of employees or contractors is disclosed or processed without a valid legal basis, triggering mandatory GDPR notification obligations. | HR data handling procedures not formally documented. No Data Protection Impact Assessment (DPIA) completed for HR data systems. ROPA (Record of Processing Activities) incomplete. | SharePoint sensitivity labels on HR document libraries. GDPR clauses in employment and contractor agreements. Legal & Partnerships team has GDPR awareness. | 2 | 4 | 8 | Medium | Treat | Document HR data processing activities in ROPA. Conduct DPIA for HR data processing systems. Deliver GDPR refresher training to HR and Legal staff. Review lawful basis for all HR data processing activities annually. | Head of Legal & Partnerships | 1 | 3 | 3 | Low | 31 Dec 2026 | Open | May 2026 | ROPA update assigned to Legal & Partnerships. DPIA scoping meeting scheduled for June 2026.

## Dashboard
Santa Laukmane — ISMS Portfolio Project — Fictional Organization
Classification: Confidential
AETHERIA INFRASTRUCTURE RESEARCH (AIR) ¦ Risk Register Dashboard
AIR-ISMS-RSK-002 v1.0 ¦ As at May 2026 ¦ 13 Risks Recorded
INHERENT RISK PROFILE (Pre-Control) |  |  |  |  | RESIDUAL RISK PROFILE (Post-Control)
Risk Level | Count | % of Total |  |  | Risk Level | Count | % of Total
Critical | 0 | 0% |  |  | Critical | 0 | 0%
High | 10 | 77% |  |  | High | 0 | 0%
Medium | 3 | 23% |  |  | Medium | 9 | 69%
Low | 0 | 0% |  |  | Low | 4 | 31%
Total | 13 | 100% |  |  | Total | 13 | 100%
TREATMENT STATUS |  |  |  |  | KEY OBSERVATIONS
Status | Count | % of Total |  |  | All 13 inherent risks are rated High or Medium — no Critical risks identified at this stage.
Open | 9 | 69% |  |  | 10 of 13 risks reduce to Medium or Low after planned controls are applied.
In Progress | 4 | 31% |  |  | RSK-005 (Incomplete Offboarding) reduces from High (16) to Low (4) — highest reduction via automation.
Accepted | 0 | 0% |  |  | RSK-003, RSK-007, RSK-009 retain a residual Impact of 5 (Severe) — likelihood reduction is the primary control lever.
Closed | 0 | 0% |  |  | 8 risks are currently Open with no treatment actions started — resource prioritisation required.
Priority treatment targets: RSK-001, RSK-002, RSK-004, RSK-005 (all High, Q3 2025 deadlines).
HIGH PRIORITY RISKS — Q3 2026 TARGETS
Risk ID | Asset | Inherent Score | Residual Score | Treatment Option | Owner | Target Date | Status
RSK-001 | Government-Affiliated Research Data | 16 | 8 | Treat | Head of IT Operations | 30 Sep 2026 | In Progress
RSK-002 | Security Configurations & Credentials | 16 | 8 | Treat | Head of IT Operations | 31 Jul 2026 | In Progress
RSK-003 | Critical Infrastructure Analysis Datasets | 15 | 5 | Treat | Head of IT Operations | 31 Aug 2026 | Open
RSK-004 | Restricted Research & AI Model Data | 16 | 8 | Treat | Head of Security & Compliance | 31 Oct 2026 | Open
RSK-005 | All Primary Assets (access vector) | 16 | 4 | Treat | Head of IT Operations | 30 Sep 2026 | Open
RSK-009 | Research Data Repositories (cloud & on-premises) | 15 | 8 | Treat | Head of IT Operations | 31 Oct 2026 | Open