## Findings Log
Santa Laukmane — ISMS Portfolio Project — Fictional Organization
AETHERIA INFRASTRUCTURE RESEARCH (AIR) ¦ Internal Audit Findings Log ¦ AIR-ISMS-AUD-001
June 2026 ¦ Classification: Confidential ¦ Owner: Head of Security & Compliance
Finding ID | Finding Type | Control Ref | Observation Summary | Responsible Owner | Target Date | Status | Date Closed | Corrective Action / Response | Verified By | Verification Date
NC-M-001 | Major Non-Conformity | 5.19 | Supplier security assessment process not implemented. Suppliers with Restricted data access have no security review. | Head of Legal & Partnerships | 31 Aug 2025 | Open |  | Develop supplier questionnaire, classify suppliers by tier, assess Tier 1 suppliers, update legacy contracts.
NC-M-002 | Major Non-Conformity | 5.34 | ROPA not completed. No DPIA conducted for PA-001, PA-002, or HR data processing. | Head of Legal & Partnerships | 31 Jul 2025 | Open |  | Complete ROPA. Conduct DPIAs for research data and HR processing. Assign Data Protection Lead.
NC-m-001 | Minor Non-Conformity | 5.17 / 8.5 | 5 accounts with SMS-only MFA (prohibited). 1 Conditional Access exclusion with no documented approval. | Head of IT Operations | 31 Jul 2025 | Open |  | Migrate SMS accounts to Authenticator. Remove/approve CA exclusion. Monthly MFA coverage reporting.
NC-m-002 | Minor Non-Conformity | 5.16 / 5.18 | 1 contractor account active 11 days post-departure. 2 of 5 sampled offboardings non-compliant. | Head of IT Operations | 30 Sep 2026 | In Progress |  | Immediately disable stale account. Automate deprovisioning. Audit all contractor accounts vs HR records.
NC-m-003 | Minor Non-Conformity | 5.18 | No annual employee access review completed. Quarterly contractor review overdue. No sign-off documentation. | Head of IT Operations | 31 Aug 2026 | Open |  | Complete in-progress contractor review with sign-off. Conduct first annual employee access review.
NC-m-004 | Minor Non-Conformity | 6.3 | 6 of 15 sampled staff have no training record. 3 contractors received no security briefing. No tracking system. | Head of Security & Compliance | 31 Aug 2026 | Open |  | Define training content set. Deliver to all untrained staff. Implement completion tracking.
NC-m-005 | Minor Non-Conformity | 8.15 / 8.16 | 3 log sources not connected to Log Analytics. 2 sources at 31-day retention. No custom alert rules. 23-min alert delay. | Head of IT Operations | 30 Sep 2026 | Open |  | Connect missing sources. Set 90-day retention. Implement custom alert rules. Define alert acknowledgement SLA.
OFI-001 | Observation | 5.7 | No threat intelligence capability or ISAC membership. Nation-state risk not formally monitored. | Head of Security & Compliance | 31 Dec 2026 | Open |  | Identify and join relevant ISAC. Establish quarterly threat briefing process.
OFI-002 | Observation | 8.23 | No web filtering solution. SmartScreen not enforced via policy. No centralised visibility. | Head of IT Operations | 31 Dec 2026 | Open |  | Evaluate and deploy Defender for Endpoint web content filtering or equivalent.
OFI-003 | Observation | 8.33 | Real Restricted research data used in test environments. No masking or anonymisation in place. | Head of AI Engineering | 31 Dec 2026 | Open |  | Develop test data management procedure. Implement masking or synthetic data for test use.
OFI-004 | Observation | 8.29 / 8.34 | No penetration test conducted or scheduled. May be required by government partner agreements. | Head of Security & Compliance | 31 Oct 2026 | Open |  | Commission external penetration test of Azure environment and key applications H2 2026.
OFI-005 | Observation | 7.10 | USB storage not restricted via Intune. No removable media policy documented. | Head of IT Operations | 31 Dec 2026 | Open |  | Implement USB restriction via Intune. Add removable media rules to Acceptable Use Policy.

## Summary
Santa Laukmane — ISMS Portfolio Project — Fictional Organization
Audit Findings Summary
AIR-ISMS-AUD-001 ¦ June 2026
Finding Type | Total | Open | In Progress | Closed
Major Non-Conformity | 2 | 2 | 0 | 0
Minor Non-Conformity | 5 | 4 | 1 | 0
Observation | 5 | 5 | 0 | 0
TOTAL | 12 | 11 | 1 | 0