## Executive Summary
Santa Laukmane — ISMS Portfolio Project — Fictional Organization
AETHERIA INFRASTRUCTURE RESEARCH (AIR)
Information Security Improvement Roadmap ¦ AIR-ISMS-RMP-001
Version 1.0 ¦ June 2026 — March 2027 ¦ Classification: Confidential
Document ID | AIR-ISMS-RMP-001
Version | 1.0
Status | Approved
Classification | Confidential
Owner | Head of Security & Compliance
Approved By | Chief Executive Officer
Roadmap Period | June 2026 — March 2027
Review Cycle | Quarterly
Target Outcome | ISO/IEC 27001:2022 Certification — Q1 2027
Source Documents | AIR-ISMS-RSK-002 Risk Register ¦ AIR-ISMS-SOA-001 SoA ¦ AIR-ISMS-AUD-001 Audit Report
ROADMAP SUMMARY
Workstream | P1 Critical | P2 High | P3 Medium | Total | Theme Colour
Access & Identity | 5 | 4 | 0 | 9
Legal & Compliance | 3 | 2 | 0 | 5
Supplier Security | 3 | 0 | 1 | 4
People & Awareness | 0 | 4 | 1 | 5
Monitoring & Detection | 0 | 4 | 1 | 5
Data Protection | 0 | 3 | 1 | 4
Infrastructure & Resilience | 2 | 2 | 1 | 5
Secure Development | 0 | 1 | 3 | 4
ISMS Governance | 4 | 1 | 2 | 7
TOTAL | 17 | 21 | 10 | 48
PRIORITY LEGEND
P1 — Critical | Must complete before external certification. Linked to Major NCRs or critical risk register items.
P2 — High | Should complete before Stage 2 audit. Linked to Minor NCRs or High-rated risks.
P3 — Medium | Planned improvement. Linked to Observations, SoA gaps, or Medium-rated risks.

## Roadmap
Santa Laukmane — ISMS Portfolio Project — Fictional Organization
AETHERIA INFRASTRUCTURE RESEARCH (AIR) ¦ Security Improvement Roadmap ¦ AIR-ISMS-RMP-001 v1.0
June 2026 – March 2027 ¦ 48 Initiatives ¦ Target: ISO/IEC 27001:2022 Certification Q1 2026
[6 empty] | Q2 2026 |  | Q3 2025 |  |  | Q4 2025 |  |  | Q1 2026
ID | Workstream | Initiative Name | Source Ref | Priority | Owner | Jun 26 | Jul 26 | Aug 26 | Sep 26 | Oct 26 | Nov 26 | Dec 26 | Jan 27 | 2026-02-27 | 2026-03-27 | Status | Notes
ACCESS & IDENTITY
AI-001 | Access & Identity | Disable stale contractor account immediately | NC-m-002 / RSK-005 | P1 | Head of IT Operations | ▶ | [9 empty] | In Progress | Account identified during internal audit. Immediate action required.
AI-002 | Access & Identity | Migrate SMS-only MFA accounts to Authenticator | NC-m-001 / RSK-002 | P1 | Head of IT Operations | ◀ | ▶ | [8 empty] | Not Started | 5 accounts using prohibited SMS MFA. Target: 100% Authenticator by 31 Jul.
AI-003 | Access & Identity | Resolve unapproved Conditional Access exclusion | NC-m-001 | P1 | Head of IT Operations | ◀ | ▶ | [8 empty] | Not Started | Remove or formally approve with compensating control and time limit.
AI-004 | Access & Identity | Audit all contractor accounts against HR records | NC-m-002 / RSK-005 | P1 | Head of IT Operations | ◀ | ▶ | [8 empty] | Not Started | Full reconciliation — identify any further stale accounts beyond the one found at audit.
AI-005 | Access & Identity | Complete Q2 contractor access review with formal sign-off | NC-m-003 | P1 | Head of IT Operations | ▶ | [9 empty] | In Progress | In-progress review must be closed with documented Asset Owner approval.
AI-006 | Access & Identity | Automate Entra ID deprovisioning via HR system integration | RSK-005 / NC-m-002 | P2 | Head of IT Operations |  | ◀ | █ | ▶ | [6 empty] | Not Started | Eliminates manual offboarding dependency. Reduces RSK-005 residual score to Low.
AI-007 | Access & Identity | Enforce device compliance Conditional Access for all accounts | RSK-010 / NC-m-001 | P2 | Head of IT Operations |  | ◀ | ▶ | [7 empty] | Not Started | All accounts — including contractors — must pass device compliance check.
AI-008 | Access & Identity | Conduct first annual employee access review | NC-m-003 | P2 | Head of IT Operations |  | ◀ | ▶ | [7 empty] | Not Started | All employee accounts. Asset Owner sign-off required. Standardised template to be used.
AI-009 | Access & Identity | Document and publish Role Access Matrix | 5.18 / AIR-ISMS-POL-002 | P2 | Head of IT Operations |  |  | ◀ | ▶ | [6 empty] | Not Started | Defines standard entitlements per role. Basis for all access reviews going forward.
LEGAL & COMPLIANCE
LC-001 | Legal & Compliance | Complete GDPR Record of Processing Activities (ROPA) | NC-M-002 / RSK-013 | P1 | Head of Legal & Partnerships | ◀ | ▶ | [8 empty] | Not Started | Covers PA-001, PA-002, HR records, M365, GitHub. GDPR Article 30 obligation.
LC-002 | Legal & Compliance | Conduct DPIA for PA-001 and PA-002 research data processing | NC-M-002 | P1 | Head of Legal & Partnerships |  | ◀ | ▶ | [7 empty] | Not Started | Research data processing involving personal data of infrastructure operators.
LC-003 | Legal & Compliance | Conduct DPIA for HR and contractor data systems | NC-M-002 / RSK-013 | P2 | Head of Legal & Partnerships |  |  | ◀ | █ | ▶ | [5 empty] | Not Started | Covers SharePoint HR libraries, employment contracts system.
LC-004 | Legal & Compliance | Assign and onboard a Data Protection Lead | NC-M-002 | P1 | Head of Legal & Partnerships | ▶ | [9 empty] | Not Started | Responsible for ongoing GDPR compliance, ROPA maintenance, and DPIA programme.
LC-005 | Legal & Compliance | Review and update legacy supplier contracts with security clauses | NC-M-001 / 5.20 | P2 | Head of Legal & Partnerships |  |  | ◀ | █ | ▶ | [5 empty] | Not Started | Prioritise contracts covering Restricted data access.
SUPPLIER SECURITY
SS-001 | Supplier Security | Develop supplier security questionnaire | NC-M-001 / RSK-008 | P1 | Head of Legal & Partnerships | ◀ | ▶ | [8 empty] | Not Started | Covers security controls, breach notification obligations, subprocessor disclosure.
SS-002 | Supplier Security | Classify all active suppliers by risk tier | NC-M-001 / 5.19 | P1 | Head of Legal & Partnerships |  | ▶ | [8 empty] | Not Started | Tier 1: Restricted/Confidential data access. Tier 2: Internal. Tier 3: Public.
SS-003 | Supplier Security | Complete security assessments for all Tier 1 suppliers | NC-M-001 / RSK-008 | P1 | Head of Legal & Partnerships |  | ◀ | ▶ | [7 empty] | Not Started | Must be complete before external certification. Mandatory NCR closure action.
SS-004 | Supplier Security | Establish annual Tier 1 supplier review cycle | 5.22 | P3 | Head of Legal & Partnerships | [5 empty] | ▶ |  |  |  |  | Not Started | Schedule annual reassessments for highest-risk suppliers from 2026.
PEOPLE & AWARENESS
PA-001 | People & Awareness | Define mandatory security awareness training content | NC-m-004 / 6.3 | P2 | Head of Security & Compliance |  | ▶ | [8 empty] | Not Started | Minimum content: data classification, phishing, incident reporting, AI tool policy.
PA-002 | People & Awareness | Deliver catch-up training to all untrained staff | NC-m-004 | P2 | Head of Security & Compliance |  |  | ▶ | [7 empty] | Not Started | 40% of sampled staff had no training record. All employees and contractors in scope.
PA-003 | People & Awareness | Implement training completion tracking system | NC-m-004 | P2 | Head of Security & Compliance |  |  | ◀ | ▶ | [6 empty] | Not Started | Microsoft Viva Learning or equivalent. Must produce auditable completion records.
PA-004 | People & Awareness | Launch annual security training cycle | 6.3 / AIR-ISMS-POL-001 | P2 | Head of Security & Compliance |  |  |  | ▶ | [6 empty] | Not Started | Schedule and communicate annual training deadlines. Link to onboarding process.
PA-005 | People & Awareness | Conduct first phishing simulation exercise | 6.3 / RSK-002 | P3 | Head of Security & Compliance |  |  |  |  | ◀ | ▶ |  |  |  |  | Not Started | Baseline measurement of phishing susceptibility. Results inform training priorities.
MONITORING & DETECTION
MD-001 | Monitoring & Detection | Set all log sources to minimum 90-day retention | NC-m-005 / 8.15 | P2 | Head of IT Operations | ◀ | ▶ | [8 empty] | Not Started | 2 sources currently at 31-day retention — below policy minimum.
MD-002 | Monitoring & Detection | Connect missing log sources to Log Analytics Workspace | NC-m-005 / RSK-006 | P2 | Head of IT Operations |  | ◀ | ▶ | [7 empty] | Not Started | SA-008 (on-premises research repositories) and 2 further sources confirmed missing.
MD-003 | Monitoring & Detection | Implement custom detection alert rules (priority scenarios) | NC-m-005 / RSK-006 | P2 | Head of IT Operations |  |  | ◀ | ▶ | [6 empty] | Not Started | Credential theft, bulk data download, after-hours privileged access, geo-anomalies.
MD-004 | Monitoring & Detection | Define and implement alert acknowledgement SLA | NC-m-005 / AIR-ISMS-POL-003 | P2 | Head of IT Operations |  |  |  | ▶ | [6 empty] | Not Started | 30-minute acknowledgement target. Escalation path if unacknowledged.
MD-005 | Monitoring & Detection | Establish quarterly alert rule review | 8.16 | P3 | Head of IT Operations |  |  |  |  | ▶ | [5 empty] | Not Started | Review and tune alert rules against current threat intelligence each quarter.
DATA PROTECTION
DP-001 | Data Protection | Approve and publish AI Tool Acceptable Use Policy | RSK-004 / 5.10 | P2 | Head of Security & Compliance |  | ◀ | ▶ | [7 empty] | Not Started | Defines permitted AI tools, prohibited uses (Restricted data), approved tools list.
DP-002 | Data Protection | Deploy endpoint DLP to block Restricted data uploads to unsanctioned services | RSK-004 / 8.12 | P2 | Head of IT Operations |  |  | ◀ | █ | ▶ | [5 empty] | Not Started | Blocks file uploads to public AI, personal cloud storage from managed endpoints.
DP-003 | Data Protection | Enable anomalous download alerting in GitHub Enterprise | RSK-007 / 8.12 | P2 | Head of AI Engineering |  |  | ◀ | ▶ | [6 empty] | Not Started | Alerts on bulk clone or download from restricted repositories.
DP-004 | Data Protection | Implement removable media restriction via Intune | OFI-005 / 7.10 | P3 | Head of IT Operations |  |  | ◀ | ▶ | [6 empty] | Not Started | Block USB storage on managed devices. Exception process for approved use cases.
INFRASTRUCTURE & RESILIENCE
IR-001 | Infrastructure & Resilience | Deploy Azure Policy to deny public blob access | RSK-003 / 8.9 | P1 | Head of IT Operations | ◀ | ▶ | [8 empty] | Not Started | Policy definition drafted — pending approval to deploy to air-prod tenant.
IR-002 | Infrastructure & Resilience | Enable Microsoft Defender for Storage | RSK-003 / 8.7 | P1 | Head of IT Operations | ◀ | ▶ | [8 empty] | Not Started | Detects anomalous access patterns on blob storage containers.
IR-003 | Infrastructure & Resilience | Implement immutable backup for on-premises repositories | RSK-009 / 8.13 | P2 | Head of IT Operations |  |  | ◀ | █ | ▶ | [5 empty] | Not Started | Solution selected. Implementation scheduled Q3. Verified restoration test in Q4.
IR-004 | Infrastructure & Resilience | Verify 100% BitLocker compliance across managed fleet | RSK-012 / 8.24 | P2 | Head of IT Operations | ◀ | ▶ | [8 empty] | Not Started | Current: 96% coverage (6 devices non-compliant). Remediate flagged devices.
IR-005 | Infrastructure & Resilience | Publish travel security briefing for field staff | RSK-012 / 7.9 | P3 | Head of IT Operations |  |  | ▶ | [7 empty] | Not Started | Covers device handling, public Wi-Fi, screen privacy at conferences.
SECURE DEVELOPMENT
SD-001 | Secure Development | Define secure development policy and coding standards | 8.25 / 8.28 | P3 | Head of AI Engineering |  |  |  | ◀ | ▶ | [5 empty] | Not Started | Covers secure coding principles, code review requirements, dependency management.
SD-002 | Secure Development | Commission external penetration test (Azure + applications) | OFI-004 / 8.29 | P2 | Head of Security & Compliance |  |  |  | ◀ | ▶ | [5 empty] | Not Started | Scope: air-prod Azure environment and key web-facing research platforms.
SD-003 | Secure Development | Implement test data masking for PA-001 / PA-002 | OFI-003 / 8.33 | P3 | Head of AI Engineering |  |  |  |  | ◀ | █ | ▶ |  |  |  | Not Started | Prevent real Restricted data being used in dev/test environments.
SD-004 | Secure Development | Implement security gates in CI/CD pipeline | 8.29 / 8.25 | P3 | Head of AI Engineering |  |  |  |  | ◀ | █ | ▶ |  |  |  | Not Started | SAST scanning, dependency vulnerability checks, secrets detection.
ISMS GOVERNANCE
IG-001 | ISMS Governance | Establish quarterly ISMS compliance review process | 5.36 / AIR-ISMS-POL-001 | P2 | Head of Security & Compliance |  |  |  | ▶ | [6 empty] | Not Started | Structured review of control effectiveness against SoA. Outputs update Risk Register.
IG-002 | ISMS Governance | Join sector threat intelligence ISAC | OFI-001 / 5.7 | P3 | Head of Security & Compliance |  |  |  | ◀ | ▶ | [5 empty] | Not Started | Critical infrastructure or research sector ISAC. Establish quarterly briefing process.
IG-003 | ISMS Governance | Deploy web content filtering (Defender for Endpoint) | OFI-002 / 8.23 | P3 | Head of IT Operations |  |  |  |  | ◀ | ▶ |  |  |  |  | Not Started | Enforce via Intune policy. Centralised visibility dashboard for Security & Compliance.
IG-004 | ISMS Governance | Conduct follow-up internal audit (NCR closure verification) | ISO 27001:2022 Clause 9.2 | P1 | Head of Security & Compliance | [5 empty] | ▶ |  |  |  |  | Not Started | Verify closure of NC-M-001, NC-M-002 and all minor NCRs before external audit.
IG-005 | ISMS Governance | Submit Stage 1 external certification audit application | ISO 27001:2022 Certification | P1 | Head of Security & Compliance | [6 empty] | ▶ |  |  |  | Not Started | Conditional on all major NCRs closed and minor NCRs on documented treatment trajectory.
IG-006 | ISMS Governance | ISO 27001:2022 Stage 1 audit (documentation review) | ISO 27001:2022 Certification | P1 | Head of Security & Compliance | [6 empty] | ◀ | ▶ |  |  | Not Started | External auditor reviews ISMS documentation. Identifies Stage 2 readiness gaps.
IG-007 | ISMS Governance | ISO 27001:2022 Stage 2 audit (on-site certification) | ISO 27001:2022 Certification | P1 | Head of Security & Compliance | [8 empty] | ◀ | ▶ | Not Started | On-site audit of ISMS implementation. Target: certification achieved by end Q1 2027.

## Pre-Certification Checklist
Santa Laukmane — ISMS Portfolio Project — Fictional Organization
ISO/IEC 27001:2022 Pre-Certification Checklist ¦ AIR-ISMS-RMP-001
Complete all items before submitting Stage 1 audit application (target: December 2025)
Ref | Gate | Required Action | Owner | Deadline | Status
G-01 | Major NCR Closure | NC-M-001 closed: Tier 1 supplier assessments complete, questionnaire in place. | Head of Legal & Partnerships | 31 Aug 2026 | ☐ Open
G-02 | Major NCR Closure | NC-M-002 closed: ROPA complete, DPIA for PA-001 and PA-002 complete. | Head of Legal & Partnerships | 31 Aug 2026 | ☐ Open
G-03 | Minor NCR Trajectory | NC-m-001: MFA remediation complete (100% Authenticator; CA exclusion resolved). | Head of IT Operations | 31 Jul 2026 | ☐ Open
G-04 | Minor NCR Trajectory | NC-m-002: Stale accounts cleared; automated deprovisioning in place or formally scheduled. | Head of IT Operations | 30 Sep 2026 | ☐ Open
G-05 | Minor NCR Trajectory | NC-m-003: Annual employee access review complete with documented sign-off. | Head of IT Operations | 31 Aug 2026 | ☐ Open
G-06 | Minor NCR Trajectory | NC-m-004: All staff trained; tracking system in place with auditable records. | Head of Security & Compliance | 31 Aug 2026 | ☐ Open
G-07 | Minor NCR Trajectory | NC-m-005: All log sources connected; 90-day retention; custom alert rules active. | Head of IT Operations | 30 Sep 2026 | ☐ Open
G-08 | Policy Framework | All six topic-specific policies approved: POL-001 through POL-006. | Head of Security & Compliance | 31 Oct 2026 | ☐ Open
G-09 | Risk Register | All High-rated risks (score ≥ 10) have approved, time-bound treatment plans. | Head of Security & Compliance | 30 Sep 2026 | ☐ Open
G-10 | Statement of Applicability | SoA reviewed and updated to reflect current implementation status. | Head of Security & Compliance | 31 Oct 2026 | ☐ Open
G-11 | Asset Inventory | Asset Inventory reviewed, confirmed current, and signed off by all Asset Owners. | Head of Security & Compliance | 30 Sep 2026 | ☐ Open
G-12 | Follow-up Internal Audit | Follow-up audit (IG-004) completed. NCR closure verified. Findings log updated. | Head of Security & Compliance | 30 Nov 2026 | ☐ Open
G-13 | Incident Response | Tabletop exercise completed (AIR-ISMS-EXR-001). Action log from exercise closed. | Head of Security & Compliance | 30 Sep 2026 | ☐ Open
G-14 | Management Review | Formal management review meeting held per ISO 27001:2022 Clause 9.3. Minutes recorded. | Chief Executive Officer | 30 Nov 2026 | ☐ Open
G-15 | External Audit Application | Stage 1 external certification audit application submitted to accredited certification body. | Head of Security & Compliance | 31 Dec 2026 | ☐ Open